## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
1 | Register | Authentication and User Management | Medium | Users create a new account using email, password, and basic personal information. The system validates email format, password strength, and email duplication before creating the account. | Iteration 1 | Pending
2 | Login | Authentication and User Management | Simple | Users log in to the system using email and password. After successful authentication, the system redirects users based on their role, such as Customer, Organizer, Staff, or Admin. | Iteration 1 | Pending
3 | Login via Google | Authentication and User Management | Medium | Customers log in quickly using their Google account. If the Google email does not exist in the system, a new Customer account may be created. | Iteration 1 | Pending
4 | Logout | Authentication and User Management | Simple | Users log out of the system. The system ends the current session and redirects users to the login page or homepage. | Iteration 1 | Pending
5 | Forgot password | Authentication and User Management | Medium | Users request a password reset when they forget their password. The system sends an email containing a reset link or verification code for creating a new password. | Iteration 1 | Pending
6 | View Profile | Authentication and User Management | Simple | Users view their personal profile information, such as full name, email, phone number, avatar, and account role. | Iteration 1 | Pending
7 | Update Profile | Authentication and User Management | Simple | Users update personal information such as full name, phone number, avatar, or other editable profile details. | Iteration 1 | Pending
8 | Change Password | Authentication and User Management | Medium | Users change their password after logging in. The system requires the current password, new password, and password confirmation. | Iteration 1 | Pending
9 | View Events | Event and Engagement Management | Medium | Customers view public events and access event details, including event name, description, date and time, location, ticket types and prices, policies, Organizer information, and event images. | Iteration 1 | Pending
10 | Search Event | Event and Engagement Management | Simple | Customers search for events by keywords such as event name, location, category, or Organizer name. | Iteration 1 | Pending
11 | Filter Event | Event and Engagement Management | Medium | Customers filter the event list by criteria such as category, date, location, price range, or event status. | Iteration 1 | Pending
12 | Book Ticket | Ticket Management | Complex | Customers select an event, ticket type, ticket quantity, or seat to create a ticket order. The system checks ticket availability before creating the order. | Iteration 2 | Pending
13 | Payment | Ticket Management | Complex | Customers pay for a ticket order using a payment method supported by the system. After successful payment, the system confirms the order and issues the tickets. | Iteration 2 | Pending
14 | View My Tickets | Ticket Management | Simple | Customers view the list of purchased tickets, including valid, used, canceled, or refund-pending tickets. | Iteration 2 | Pending
15 | View Ticket Detail | Ticket Management | Medium | Customers view details of a purchased ticket, including event information, ticket type, ticket code, QR code, ticket status, and attendee information. | Iteration 2 | Pending
16 | Download Ticket | Ticket Management | Simple | Customers download tickets to their device as a PDF or image for use when attending the event. | Iteration 2 | Pending
17 | Chat with AI Assistant | Event and Engagement Management | Complex | Customers interact with an AI assistant to ask questions, discover suitable events, receive event and ticket recommendations, check ticket availability and pricing, and receive support throughout the ticket booking, payment, check-in, and refund processes. | Iteration 3 | Pending
18 | Provide Event Feedback | Event and Engagement Management | Simple | Customers provide ratings and comments after attending an event. The feedback helps Organizers monitor event quality. | Iteration 1 | Pending
19 | Request Organizer Role | Authentication and User Management | Medium | Customers request to become an Organizer by providing personal or organization information for Admin review and approval. | Iteration 1 | Pending
20 | Create Event | Event and Engagement Management | Complex | Organizers create a new event with information such as event name, description, date and time, location, category, images, and related policies. | Iteration 1 | Pending
21 | View Own Event List | Event and Engagement Management | Medium | Organizers view their created events and access detailed information, including event details, tickets, revenue, orders, attendees, operation status, and event status. | Iteration 1 | Pending
22 | Update Event | Event and Engagement Management | Complex | Organizers update event information when the event is still in an editable status. Some important changes may require Admin review again. | Iteration 1 | Pending
23 | Publish Event | Event and Engagement Management | Medium | Organizers submit an event for publishing or approval before it becomes visible to Customers. The system checks required information before publishing. | Iteration 2 | Pending
24 | Cancel Event | Event and Engagement Management | Simple | Organizers cancel an event when necessary. The system updates the event status, notifies ticket buyers, and supports refund processing if applicable. | Iteration 2 | Pending
25 | Create Ticket Type | Ticket Management | Medium | Organizers create ticket types for an event, such as Standard, VIP, Early Bird, or Free tickets, including price, quantity, and sales period. | Iteration 2 | Pending
26 | View Ticket Types | Ticket Management | Medium | Organizers view ticket types configured for their events and access details including price, issued quantity, sold quantity, sales period, and active status. | Iteration 2 | Pending
27 | Update Ticket Type | Ticket Management | Medium | Organizers update ticket type information such as ticket name, price, quantity, description, or sales period if the edit conditions are met. | Iteration 2 | Pending
28 | Delete Ticket Type | Ticket Management | Simple | Organizers delete a ticket type when it has no transactions or customer bookings. | Iteration 2 | Pending
29 | Create Venue | Venue Management | Medium | Organizers create venue information, including venue name, address, capacity, and space description. | Iteration 1 | Pending
30 | View Venues | Venue Management | Medium | Organizers view their created venues and access details including address, capacity, description, and related seat maps if available. | Iteration 1 | Pending
31 | Update Venue | Venue Management | Medium | Organizers update venue information such as name, address, capacity, or venue description. | Iteration 1 | Pending
32 | Delete Venue | Venue Management | Simple | Organizers delete a venue if it is not being used by an active or ticket-selling event. | Iteration 1 | Pending
33 | Create Seat Map | Venue Management | Complex | Organizers create a seat map for a venue or event, including zones, rows, seat numbers, and seat statuses. | Iteration 2 | Pending
34 | View Seat Map | Venue Management | Medium | Organizers view the configured seat map to check layout, seating zones, and seat allocation status. | Iteration 2 | Pending
35 | Update Seat Map | Venue Management | Complex | Organizers update a seat map when no ticket bookings are affected by the changes. | Iteration 2 | Pending
36 | Delete Seat Map | Venue Management | Medium | Organizers delete a seat map if it has not been applied to an event that is selling tickets or already has transactions. | Iteration 2 | Pending
37 | Create Promo Code | Venue Management | Medium | Organizers create promo codes for an event, including discount type, discount value, usage limit, validity period, and application conditions. | Iteration 3 | Pending
38 | View Promo Codes | Venue Management | Medium | Organizers view promo codes created for their events and access details including discount value, application conditions, usage count, and active status. | Iteration 3 | Pending
39 | Update Promo Code | Venue Management | Medium | Organizers update promo code information when the code is still within the allowed editing conditions. | Iteration 3 | Pending
40 | Delete Promo Code | Venue Management | Simple | Organizers delete or deactivate promo codes that are no longer in use. | Iteration 3 | Pending
41 | View Orders | Operations Management | Medium | Organizers view orders for their events and access details including buyer information, tickets, payment details, promo code, order status, and processing history. | Iteration 2 | Pending
42 | View Attendee List | Operations Management | Medium | Organizers view the attendee list generated from sold tickets or valid event tickets. | Iteration 2 | Pending
43 | Export Attendee List | Operations Management | Medium | Organizers export the attendee list as an Excel or CSV file for check-in, event operations, or reporting. | Iteration 3 | Pending
44 | Assign Staff to Event | Operations Management | Medium | Organizers assign Staff to support a specific event, such as check-in or on-site ticket sales. | Iteration 1 | Pending
45 | Remove Staff from Event | Operations Management | Simple | Organizers remove Staff from an event when they are no longer involved in operations or were assigned incorrectly. | Iteration 1 | Pending
46 | View Check-in Dashboard | Operations Management | Medium | Organizers monitor event check-in status, including checked-in tickets, unchecked tickets, invalid tickets, and attendance rate. | Iteration 2 | Pending
47 | View Revenue Dashboard | Financial Management | Medium | Organizers view an overview of event revenue, including ticket sales revenue, order count, platform fees, and estimated payout amount. | Iteration 3 | Pending
48 | View Ticket Sales Analytics | Financial Management | Medium | Organizers view ticket sales analytics by time, ticket type, sold quantity, and event occupancy rate. | Iteration 3 | Pending
49 | View Feedback Report | Event and Engagement Management | Simple | Organizers view Customer feedback reports after the event, including ratings, comments, and satisfaction level. | Iteration 1 | Pending
50 | Generate Financial Summary with AI | Financial Management | Complex | Organizers use AI to generate an event financial summary, including revenue, sold tickets, platform fees, and overall financial insights. | Iteration 3 | Pending
51 | View Assigned Event List | Operations Management | Simple | Staff view events assigned to them by the Organizer and their assigned working gate and responsibilities for each event. | Iteration 3 | Pending
52 | Scan QR Ticket | Operations Management | Medium | Staff scan the QR code on an attendee’s ticket. The system checks whether the ticket is valid, belongs to the correct event, and has not been used. | Iteration 3 | Pending
53 | Check-in Ticket | Operations Management | Medium | Staff confirm check-in for a valid ticket. After successful check-in, the system updates the ticket status to used. | Iteration 3 | Pending
54 | Search Ticket for Manual Check-in | Operations Management | Simple | Staff search for tickets manually by ticket code, email, phone number, or buyer information when QR scanning is not possible. | Iteration 3 | Pending
55 | Manual Check-in Ticket | Operations Management | Simple | Staff perform manual check-in after finding a valid ticket and verifying attendee information. | Iteration 3 | Pending
56 | Book Ticket On-site | Ticket Management | Complex | Staff create on-site ticket orders for walk-in customers at the event. Staff select ticket type, ticket quantity, and enter customer information if needed. | Iteration 3 | Pending
57 | Confirm On-site Payment | Ticket Management | Medium | Staff confirm on-site payment by cash, bank transfer, or another supported method. After confirmation, the system issues tickets to the customer. | Iteration 3 | Pending
58 | View Account List | Authentication and User Management | Medium | Admin view the list of accounts in the system, including Customers, Organizers, Staff, and administrative accounts if they have proper permission. | Iteration 1 | Pending
59 | Lock User Account | Authentication and User Management | Simple | Admin lock accounts that violate policies or show risk indicators. Locked accounts cannot log in or use main system functions. | Iteration 1 | Pending
60 | Unlock User Account | Authentication and User Management | Simple | Admin unlock accounts after the issue has been reviewed or resolved. | Iteration 1 | Pending
61 | Review Organizer Request | Authentication and User Management | Medium | Admin reviews and processes requests to become an Organizer by approving or rejecting them based on registration information and eligibility conditions. If rejected, the Admin provides a reason for the rejection. | Iteration 1 | Pending
62 | Review Event | Event and Engagement Management | Medium | Admin reviews and approves or rejects events submitted by Organizers before publication. | Iteration 2 | Pending
63 | Hide Event | Event and Engagement Management | Simple | Admin hide a published event when violations, complaints, or issues requiring further review are detected. | Iteration 2 | Pending
64 | Create Event Category | Event and Engagement Management | Simple | Admin create event categories such as music, conference, sports, education, or entertainment to classify events on the platform. | Iteration 1 | Pending
65 | View Event Category List | Event and Engagement Management | Simple | Admin view the list of existing event categories in the system. | Iteration 1 | Pending
66 | Update Event Category | Event and Engagement Management | Simple | Admin update the name, description, or active status of an event category. | Iteration 1 | Pending
67 | Delete Event Category | Event and Engagement Management | Simple | Admin delete an event category if it has not been used or is no longer suitable. | Iteration 1 | Pending
68 | View Analytics Dashboard | Financial Management | Medium | Admin view a platform-wide analytics dashboard, including users, events, orders, revenue, and transaction activities. | Iteration 3 | Pending
69 | Configure Platform Policy | Financial Management | Complex | Admin configure platform policies such as refund rules, payout rules, event approval, service fees, and Organizer regulations. | Iteration 3 | Pending
70 | View Subscription | Financial Management | Simple | Admin, Organizer view the list and details of subscription plans available on the platform. | Iteration 1 | Pending
71 | Create Subscription | Financial Management | Medium | Admin create a new subscription plan with pricing, duration, and included features. | Iteration 2 | Pending
72 | Update Subscription | Financial Management | Medium | Admin update subscription plan information such as price, duration, or benefits. | Iteration 2 | Pending
73 | Delete Subscription | Financial Management | Simple | Admin delete or deactivate a subscription plan that is no longer used. | Iteration 2 | Pending
74 | Request Ticket Refund | Financial Management | Medium | Customer submits a refund request for a ticket/order that meets the Event's Refund Policy. | Iteration 3 | Pending
75 | View Refund Request | Financial Management | Simple | Organizer views refund requests and details for their Events. | Iteration 3 | Pending
76 | Process Refund Request | Financial Management | Complex | Organizer approves or rejects refund requests and processes approved refunds through the configured payment gateway/account. | Iteration 3 | Pending
77 | Generate Event Content with AI | Operations Management | Complex | Organizer provides basic Event information, and AI generates suggested title, description, and content for review and editing. | Iteration 3 | Pending
78 | AI-Assisted Event Review | Operations Management | Complex | AI analyzes Organizer-submitted events for completeness, consistency, and policy risks, providing alerts and approval recommendations to support the Admin’s final decision. | Iteration 3 | Pending
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | [6 empty] | Open
2 | [6 empty] | Open
3 | [6 empty] | Open
4 | [6 empty] | Open
5 | [6 empty] | Open
6 | [6 empty] | Open
7 | [6 empty] | Open

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open